## Risk Data
Risk ID | Description | Initial Probability | Occurrence Time (Day) | Cost PERT (min) | Cost PERT (most likely) | Cost PERT (max) | Delay PERT (min) | Delay PERT (most likely) | Delay PERT (max) | Dependent Risks | Probability Adjustment
R001 | Threat 1 - Description | 0.25 | 16 | 8763,7 | 11425,0 | 13715,6 | 10 | 10 | 10 | R015 | 0.15
R002 | Threat 2 - Description | 0.26 | 57 | 2895,6 | 7707,9 | 10269,9 | 13 | 23 | 32 | R010, R008 | 0.19
R003 | Threat 3 - Description | 0.37 | 76 | 9663,3 | 9956,9 | 10686,3 | 12 | 13 | 14 | R012, R014 | 0.18
R004 | Opportunity 4 - Description | 0.11 | 89 | -8871,2 | -8880,4 | -9208,7 | -6 | -6 | -6 | R007, R009, R005 | -0.2
R005 | Threat 5 - Description | 0.48 | 93 | 6114,5 | 11201,1 | 12815,2 | 15 | 26 | 32
R006 | Threat 6 - Description | 0.44 | 101 | 7132,5 | 8347,8 | 9427,2 | 14 | 19 | 28 | R010, R014, R008 | 0.06
R007 | Opportunity 7 - Description | 0.19 | 221 | -769,5 | -931,2 | -1654,1 | -5 | -7 | -7 | R015, R008 | -0.07
R008 | Threat 8 - Description | 0.25 | 245 | 9645,0 | 14308,7 | 16836,2 | 6 | 7 | 26 | R015, R013 | 0.06
R009 | Threat 9 - Description | 0.14 | 265 | 4401,5 | 12691,8 | 15272,8 | 5 | 12 | 27 | R013, R015, R012 | 0.19
R010 | Threat 10 - Description | 0.27 | 274 | 9689,1 | 12090,5 | 12389,7 | 5 | 6 | 16 | R014, R011, R015 | 0.06
R011 | Threat 11 - Description | 0.31 | 281 | 7082,6 | 7450,1 | 7599,3 | 20 | 26 | 28 | R013, R012, R015 | 0.13
R012 | Threat 12 - Description | 0.13 | 281 | 8044,8 | 12026,2 | 18269,0 | 18 | 26 | 29 | R014, R015 | 0.07
R013 | Threat 13 - Description | 0.45 | 284 | 2374,1 | 6563,2 | 9374,0 | 14 | 21 | 34
R014 | Opportunity 14 - Description | 0.11 | 323 | -1527,5 | -4431,9 | -4700,4 | 0 | -3 | -7
R015 | Threat 15 - Description | 0.44 | 361 | 4761,6 | 5682,6 | 7432,3 | 9 | 19 | 34
Note on D1: Days since project start
Note on E1: Cost values in monetary units. min: Minimum, most likely: Most likely, max: Maximum
Note on H1: Delay values in whole days. min: Minimum, most likely: Most likely, max: Maximum